## Slide 1
CARE 4 U
A HSS Management System
Presented by “Team Diplomats”

## Slide 2
v
OUR
TEAM
Abdullah Basar Maruf
CSE06307404
Nur Mohammed Rana
CSE06307478
Tanvir Ahmed Rahat
CSE06307397
Team Diplomats
Khadija Akhter Rono
CSe06307480

## Slide 3
OUR
AGENDA
Easy to Access
Vast Opportunities
Provide Quality Service
Solving Real Life Problem
Sufficient Resource for Collecting Data

## Slide 4
INTRODUCTION
What is HSS
Taking care by Management Committee which is a group of people who are elected by the society residents to handle all the apartment society operations.
Types of HSS
Ownership housing society
Joint ownership
Other co-operative housing society.
Provide Service for this
Project
In order to deliver the highest standard of a service and provide excellence.

## Slide 5
01
24/7 Customer Service
02
Web Based UI
03
Secured Registration Process
Features

## Slide 6
04
Elite Membership facilities
05
Customer Feedback Review
06
One call away service
Features

## Slide 7
Feasibilities
Technical
Economical
Operational
Feasibilities for this project

## Slide 8: Technical Feasibilities
Hardware
  Laptop & PC
  Internet Connection
Software
  Open Source Software
  OS as Windows
Technology
  Up to date
  User friendly

## Slide 9: Economical Feasibilities
Availability of software and hardware
Cost efficient
Low Budget
Data Collection & information gathering cost
Technical cost
Other cost

## Slide 10: Operational feasibility
User level
  Amateur
User Interface
  User-friendly, efficient & simple
Troubleshooting
  Proper actions to identify errors
Maintenance
  Optimized short run

## Slide 11: Project Scheduling
Analysis
Planning
Construction
Deployment

## Slide 12: Analysis
Activity | Description | Precedence | Time (in week)
01 | Project Study & Goal Setup | none | 01
02 | Meeting with Clients | 01 | 01

## Slide 13: Planning
Activity | Description | Precedence | Time (in week)
03 | Collecting requirements | 01 | 01
04 | Detailed requirements | 02 | 1
05 | Proposition of requirements | 02 | 1

## Slide 14: Construction
Activity | Description | Precedence | Time (in week)
06 | Database Development | 05 | 03
07 | UI Design | 05 | 02
08 | Coding | 07 | 03

## Slide 15: Deployment
Activity | Description | Precedence | Time (in week)
09 | Software Testing | 08 | 02
10 | Feedback & Launching | 09 | 01

## Slide 16: Gantt Chart

## Slide 17: Risk Analysis
Backup for database
Secured Database & Registration form with secured process
Timing Commitment
Hardware backup

## Slide 18
v
Team Diplomats
CONTACT US
abdullahmaruf86@gmail.com
THANK YOU